## Funtions based on Roles
Time range | Sprint 0: 27-Sep System modeling –part 1
Role | Basic Functions | Responsible Members | Status 0: Not started 1: Started but not finished 2: Finished
Buyer | Buyer Module Requirements Specification,Backlog,Architecture,story points and all stories ordered,Tools and technologies to be used | Sreekar, Akshay | 0
Seller | Seller Module Requirements Specification,Backlog,Architecture,story points and all stories ordered,Tools and technologies to be used | Yunwei Jiang, JingZhou Hu | 0
Main WebSite and Admin | Main WebSite and Admin Module Requirements Specification,Backlog,Architecture,story points and all stories ordered, Tools and technologies to be used | Brian Juan Hemanshu, Joshi Ashita, Kalidindi | 0
All users | The completed product backlog, with story points and all stories ordered | All members | 0
All users | PPT | All members | 0
All users | High-level software architecture | All members | 0
All users | Tools and technologies to be used | All members | 0
Time range | Sprint 1: 11-Oct
Role | Basic Functions | Responsible Members | Status 0: Not started 1: Started but not finished 2: Finished
Seller | User registration User profile editting | Yunwei Jiang Jingzhou Hu | 0
Seller | posting goods Edit goods Basic Database CRUD operations | Yunwei Jiang Jingzhou Hu | 0
All users | Main page prototype | Yunwei Jiang Jingzhou Hu | 0
Seller | Seller Database Design | Yunwei Jiang Jingzhou Hu | 0
Time range | Sprint 2: 1-Nov
Role | Basic Functions | Responsible Members | Status 0: Not started 1: Started but not finished 2: Finished
Time range | Sprint 3: 15-Nov
Role | Basic Functions | Responsible Members | Status 0: Not started 1: Started but not finished 2: Finished
Time range | Software Testing & Evolution: 29-Nov
Role | Basic Functions | Responsible Members | Status 0: Not started 1: Started but not finished 2: Finished
Time range | Final Presentations: 6-Dec
Role | Basic Functions | Responsible Members | Status 0: Not started 1: Started but not finished 2: Finished

## General Functions
General Functions | Responsible Members | Status 0: Not started 1: Started but not finished 2: Finished