## Funtions based on Roles
Role | Basic Functions | Responsible Members | Status 0: Not started 1: Started but not finished 2: Finished
Time range | Sprint 0: 27-Sep System modeling –part 1
| Buyer Module Requirements Specification,Backlog,Architecture,Database Desgin | Sreekar, Akshay | 0
| Seller Module Requirements Specification,Backlog,Architecture,Database Desgin | Yunwei Jiang, JingZhou Hu | 0
| Main Page Requirements Specification,Backlog,Architecture,Database Desgin; Admin Module Requirements Specification,Backlog,Architecture,Database Desgin | Brian Juan Hemanshu, Joshi Ashita, Kalidindi | 0
PPT
Time range | Sprint 1: 11-Oct
Seller | User registration User profile editting | Yunwei Jiang Jingzhou Hu | 0
Seller | posting goods Edit goods Basic Database CRUD operations | Yunwei Jiang Jingzhou Hu | 0
All users | Main page prototype | Yunwei Jiang Jingzhou Hu | 0
Seller | Seller Database Design | Yunwei Jiang Jingzhou Hu | 0
Time range | Sprint 2: 1-Nov
Time range | Sprint 3: 15-Nov
Time range | Software Testing & Evolution: 29-Nov
Time range | Final Presentations: 6-Dec

## General Functions
General Functions | Responsible Members | Status 0: Not started 1: Started but not finished 2: Finished