## Sheet1
Order | User Stories | Tasks | Member in charge | Time | Status (0 = not started 1 = working on 2 = finished)
1 | As a buyer, I want to login to the web app , so that I can view, compare and buy items ment for selling. | Coding: Implement Database access to general account table, account validation, update account status. |  |  | 0
|  | Coding: Implement Database access to buyer profile table, update account status. |  |  | 0
|  | Testing |  |  | 0
2 | As a buyer, I want to give reviews and ratngs to buyer and his product. | Design product review table |  |  | 0
|  | Coding: Design and Implement product detail page that shows all product information, and product rating functions . |  |  | 0
|  | Coding: Implement Database access and response to user's CRUD operation in product page. |  |  | 0
|  | Testing |  |  | 0
3 | As a buyer, I want to have an opton to share the product details via mail/twiter etc. | Coding: Implement share product via mail/twitter function. |  |  | 0
|  | Testing |  |  | 0
4 | As a buyer, I want to get details of the product, so that I can compare it with my requirement and I want to add the product to my cart or whishlist. | Design buyer cart table |  |  | 0
|  | Coding: Design and Implement buyer cart page |  |  | 0
|  | Coding: Implement Database access and response to user's CRUD operation in product page. |  |  | 0
|  | Testing |  |  | 0
5 | As a buyer, I want to know if the resale product is having any ﬂaws, so that I know the product well and bid accordingly. | Bidding system function: Should discuss with Team1 and decide whether to do this. |  |  | 0
0
0
0
6 | As a buyer, I want to know other bids for the product, so that I can bid higher to buy the product. | Bidding system function: Should discuss with Team1 and decide whether to do this. |  |  | 0
0
0
6 | As a buyer, I want a secured way of payment. | Payment function: Should discuss with Team1 and decide whether to do this. Because we probably won't have the authorization to access any bank account. |  |  | 0
0
0