## Sheet1
Order | User Stories | Tasks | Member in charge | Time | Status (0 = not started 1 = working on 2 = finished)
1 | All Users: Login/out Seller/Buyer Registration | DataBase Design: General Account Table for all users, Seller Profile and Buyer Profile table, Admin table.Finish the SQL script. | Yunwei Jiang Brian Juan |  | 2
|  | Coding: Implement Database access to related account table, account status checking and update. |  |  | 0
|  | Coding: Design and implement Login and registration page for seller and buyer. |  |  | 0
|  | Testing |  |  | 0
2 | All Users: Student Mart Main Page | DataBase Design:product table, order table, item table. Finish the SQL script. | Yunwei Jiang |  | 2
|  | Coding: Implement Database access to product table |  |  | 0
|  | Coding: Design and implement front end page to show the product catalog, product information(picture and seller name, etc.). |  |  | 0
|  | Testing |  |  | 0
3 | As a seller , I want display picture for my account and add details like name, Contact no. (Optional) for buyers to view and contact the seller. | Database Desgin: Seller Profile table. | Jingzhou Hu |  | 1
|  | Coding: Design and Implement Seller Profile Front End page | Yunwei Jiang |  | 1
|  | Coding: Implement Database access and response to user's CRUD operation in Seller Profile Front End page. | Yunwei Jiang |  | 1
|  | Testing | Yunwei Jiang |  | 0
4 | As an Admin, I want to be able to remove items from stores so that no illegal/inappropriate item will be allowed in the store. | Coding: Implement Database access to general account table, account validation, update account status. |  |  | 0
|  | Coding: Implement Database access to related account table, remove data. |  |  | 0
|  | Coding: Implement Admin Page including seller products check, removing functions.(In sprint 1 this could be just a prototype, should continue developing in next sprint). |  |  | 0
|  | Testing |  |  | 0
5 | As a buyer, I want to login to the web app , so that I can view, compare and buy items ment for selling. | Coding: Implement Database access to general account table, account validation, update account status. |  |  | 0
|  | Coding: Implement Database access to buyer profile table, update account status. |  |  | 0
|  | Testing |  |  | 0