## Sheet1
Order | User Stories | Tasks | Member in charge | Time | Status (0 = not started 1 = working on 2 = finished)
1 | As an Admin, I want to be able to remove items from stores so that no illegal/inappropriate item will be allowed in the store. | Coding: Implement Database access to general account table, account validation, update account status. |  |  | 0
|  | Coding: Implement Database access to related account table, remove data. |  |  | 0
|  | Testing |  |  | 0
2 | As an Admin, I want to be able to ban users that have scammed/sold fake items on the store | Database Desgin: Seller/Buyer Profile table. |  |  | 0
|  | Coding: Implement Database access and update the access right of user |  |  | 0
|  | Testing |  |  | 0
3 | As an Admin, I want to be able to see a admin page which gives information on how many people visited the site. | Database Desgin: counting of user |  |  | 0
|  | Coding: Design and Implement how to count and return result in Database. |  |  | 0
|  | Coding: Implement illustration of this task. |  |  | 0
|  | Testing |  |  | 0
4 | As an Admin, I want to be able to chat with any users who may have issues on the site via message api | Coding: Design and Implement the chating system |  |  | 0
|  | Coding: Implement a brif UI of chating |  |  | 0
|  | Testing |  |  | 0
5 | As an Admin, I want to be able to email all users information about the site such as maintenance or any special promos. | Coding: Design and Implement thow to email user. |  |  | 0
0
|  | Testing |  |  | 0