## Sheet1
Order | User Stories | Tasks | Member in charge | Time | Status (0 = not started 1 = working on 2 = finished)
1 | As a seller , I want display picture for my account and add details like name, Contact no. (Optional) for buyers to view and contact the seller.(Continue from Sprint 1) | Database Desgin: Seller Profile table. | Yunwei Jiang Jingzhou Hu |  | 1
|  | Coding: Design and Implement Seller Profile Front End page | Yunwei Jiang Jingzhou Hu |  | 1
|  | Coding: Implement Database access and response to user's CRUD operation in Seller Profile Front End page. | Yunwei Jiang Jingzhou Hu |  | 1
|  | Testing | Yunwei Jiang Jingzhou Hu |  | 1
2 | As a seller, I want to display the original price of the Goods and selling price, I want to display if the product is sold or not. | Database Desgin: product transaction table and profit table. | Yunwei Jiang Jingzhou Hu |  | 0
|  | Coding: Design and Implement profit and transaction status page. | Yunwei Jiang Jingzhou Hu |  | 0
|  | Coding: Implement Database access and response to user's CRUD operation from profit and transaction status page. | Yunwei Jiang Jingzhou Hu |  | 0
|  | Testing | Yunwei Jiang Jingzhou Hu |  | 0
3 | As an Admin, I want to be able to see a admin page which gives information on how many people visited the site. | Database Desgin: counting of user | Brian Juan |  | 1
|  | Coding: Design and Implement how to count and return result in Database. | Brian Juan |  | 1
|  | Coding: Implement illustration of this task. | Brian Juan |  | 1
|  | Testing | Brian Juan |  | 1