## Sheet1
Order | User Stories | Tasks | Member in charge | Time | Status (0 = not started 1 = working on 2 = finished)
1 | As a Seller, I want to Register/ Login into my account | Coding: Implement Database access to general account table, account validation, update account status. |  |  | 0
|  | Coding: Implement Database access to seller account table, update account status. |  |  | 0
|  | Testing |  |  | 0
2 | As a seller , I want display picture for my account and add details like name, Contact no. (Optional) for buyers to view and contact the seller. | Database Desgin: Seller Profile table. |  |  | 0
|  | Coding: Design and Implement Seller Profile Front End page |  |  | 0
|  | Coding: Implement Database access and response to user's CRUD operation in Seller Profile Front End page. |  |  | 0
|  | Testing |  |  | 0
3 | As a seller, I want to add pictures , Videos and description of the Goods I would like to sell. | Database Desgin: Products table. |  |  | 0
|  | Coding: Design and Implement Seller Products management, product information editing page. |  |  | 0
|  | Coding: Implement Database access and response to user's CRUD operation from product page. |  |  | 0
|  | Testing |  |  | 0
4 | As a seller, I want to display the original price of the Goods and selling price, I want to display if the product is sold or not. | Database Desgin: product transaction table and profit table. |  |  | 0
|  | Coding: Design and Implement profit and transaction status page. |  |  | 0
|  | Coding: Implement Database access and response to user's CRUD operation from profit and transaction status page. |  |  | 0
|  | Testing |  |  | 0
5 | As a seller I should be able to report to admin about my questions | Coding: Design and Implement admin contact page. Including question editing and commit. |  |  | 0
0
|  | Coding: Implement Database access to admin question table. |  |  | 0
|  | Testing |  |  | 0
6 | As a seller, I want to have Payment Gateway to sell the Goods . | Coding: Design and Implement payment gateway page. |  |  | 0
|  | Coding: Implement Database access and response to user's CRUD operation from product payment gateway page. |  |  | 0
|  | Testing |  |  | 0